## Individuals in Key groups
Communication Plan, Draft 1.0 Dated 12 02 2021
INDIVIDUALS/ GROUPS
Key groups | Multiple role | Further action required to identify? | Responsibility | Progress
Project sponsors
Lucy Butler (West Sussex DCS)
Peter Sandiford (CEO ICHA)
Project Board
Peter Sandiford – Chief Executive ICHA (Co-Sponsor) | x | no
Harvey Gallagher – Chief Executive NAFP |  | no
Matt Dunkley, DCS Kent |  | no
Alison Jeffrey, DCS Portsmouth |  | no
Mac Heath, DCS Milton Keynes |  | no
Andrea King – Local Authority Adviser, NHS England |  | no
Mark Evans, Project Lead |  | no
Rosemary Perry, Project Manager |  | no
Project team
Mark Evans, Project Lead (SESLIP), Workstream Lead - Co-produced framework including outline business Case | x | no
Rosemary Perry, Project Manager (SESLIP), Workstream Lead - Project Management | x | no
Sue Thompson, Data and Business Processes (SESLIP) |  | no
Leonie Cowen, Solicitor (LeC) - Specialist Legal and Procurement Adviser, Workstream Lead - Legal & Procurement Frameworks/Tools |  | no
Andrew Rome - Specialist Financial Adviser |  | no
Luke Rodgers - The Care Leaders, Facilitator of user involvement/engagement, Workstream Lead - User Participation |  | no
Isabelle Gregory (SESLIP) - Communications Lead, Workstream Lead - Communications and Document Management |  | no
Liz Cooper - Independent Children's Homes Association (LiC) |  | no
Susan Tanner - West Sussex lead |  | no
Sivay Heer - Milton Keynes lead |  | no
Christy Holden - Kent lead |  | no
Caroline Smith - Kent lead |  | no
Hayden Ginns - Portsmouth lead |  | no
Stephen Humphries - WSCC link procurement/commissioning |  | no
Project team colleague decision-makers and influencers
4 x legal/ finance |  | Yes - via LA Project team reps | RP | Requested but no confirmed names yet
4 x commissioning (if different from Project Team) |  | Yes - via LA Project team reps | RP | Requested but no confirmed names yet
Stakeholder Groups
Looked After Children |  | No
LA Representatives: DCS and Commissioners' Network
DCS (Key group)
Commissioners' Network |  | No | IG | Network representatives self-identified (7 to date representing 6 authorities)
Providers' Representatives
Providers' Representatives |  | no - accessed through ICHA and NAFP | LiC
Providers Senior Representatives (Key group) |  | no | PS/HG
SESLIP (Key group) |  | no
DfE (Key group) |  | no
Market
Individual Providers |  | No individuals identified | Due process/IG/LeC

## Key groups
Communications plan
Status - Version 1.0
IG 12 02 2021 |  | Please note exact comunication requirments for any elements are not yet known as their development forms part of the project.
Group | Sub-group | Communication objective | Direction | Phase | Mechanism/ material | Source | Frequency
Project sponsors | Project sponsors | Updates the Key Groups (LA DCS, Providers Senior Reps, SESLIP, DfE) | From | All | SESLIP and LAs via weekly briefing and quarterly highlight report; Lucy will also update DCSs at their regular meeting; Provider organisations via PS regular communications | LB/PS/RP | As required
Project Board | Project Board | Ensures that all memoranda of understanding and data sharing protocols are in place;Ensures that regular reporting is submitted to the DfE;Develops and signs off any funding bids for the next stage of the project | From | All | Various | RP/ME/SH | As required
Project team | Project team | Various | To & From | All | Email; meetings;password-protected area of SESLIP website (launch date Jan 29 21) | All | As required
Project team colleague decision-makers and influencers | Project team colleague decision-makers and influencers | Ensure project LAs internal corporate functions are ready to move into formal procurement processes at appropriate stage | To | All | Tbc - awaiting input from LeC/RP/ME/ AR | ME | Variable
Looked After Children | Looked After Children | Input into the project to maximise positive impact on their outcomes | To & From | Feb/ March onwards | Media tbc | LR | tbc
LA Representatives: DCS, ADs and Commissioners' Network | DCS (Key group) | ensuring that all organisations are engaged and active in the project | To | All | Public-facing page of SESLIP website; updates from LB, DCS Sponsor, weekly briefing and quarterly highlight report | IG,LB,RP,ME | various
| Assistant Directors - Safeguarding | Update on project progress | To | All | Mark newsletter/ quarterly meetings | ME | Ad hoc
| Commissioners' Network | Acts as link between project, local authority and providers; ensures project work is undertaken in LAs and providers; updates the project on risks and issues | To, with some feedback potential | All | Public-facing page of SESLIP website; update emails; limited number of meetings/ feedback sessions (tbc) | IG | monthly/ according to usefulness
Providers' Representatives | Providers' Representatives | Acts as link between project, local authority and providers; ensures project work is undertaken in LAs and providers; updates the project on risks and issues | To | All | Accessed initially through the associations – ICHA and NAFP | LiC/IG | As per LiC acitivity
| Providers Senior Representatives (Key group) | Ensuring that all organisations are engaged and active in the project | To & From | All | tbc | PS/ HG
SESLIP (Key group) | SESLIP (Key group) | Ensuring that all organisations are engaged and active in the project | To | All | Public-facing page of SESLIP website, RT regular newsletters | RT/IG | As required
DfE (Key group) | DfE (Key group) | Formal communication requirements as grant conditions – regular feedback, reporting on objectives and KPIs. DfE to inform Project about progress on other projects in the programme and sharing learning. | To & From | All | Email/ meetings | RP/ME and WSCC (LB),PS, DfE. | As required
Market | Market 1 |  | To & From | tbc | Consultation documents | LeC/RP/ME/IG/AR | As required
| Market 2 |  | To | Final | Specification documents | LeC/RP/ME/IG/AR | As required